## Slide 1
SOFIA
SITR/SSSC
Program Status
Robert Meyer
Program Manager
May 10/11, 2011
SS1
Orion Image

## Slide 2: Significant Progress!!! 1 of 2
Short Science I (FORCAST) & Short Science II (GREAT) completed on schedule!
Flew German journalist and had a visit from NBC national reporter, Tom Costello
  Article in major German newspaper
  Expect coverage from NBC on National news and Today show
RVSM certification received, can now fly in National Airspace System (NAS)!
  Not constrained to Whiskey area. Have been flying in CONUS
Basic Science I, first competed science with FORCAST started ahead of schedule on May 5, 2011!
Next generation science instrument AO release very soon
Airborne Ambassador program accelerated, first teachers fly this summer
June 8th media event at DAOF (science & education theme)
Considering Pluto occultation late June, if schedule holds
  Ted Dunham to use GTO
Image size measured at about 4 1/2 arcsec D80, exceeds early science requirement

## Slide 3: Significant Progress!!! 2 of 2
Working on initial pre-cooling (LN2) for late in Basic Science I
  Cooling to about 0 deg C, until after segment III downtime (additional insulation)
Deployment to Germany scheduled for mid September.
  Possible stop in Washington DC on return
Active mass dampers will be ground tested this summer and flown in Fall
Accelerated HIPO & FLITCAM commissioning and they are to be used this fall for TA characterization and V&V flights
Segment 3 Planning is progressing well
  Many procurements awarded
  Down time starts mid November 2011
Program making excellent progress, full summer of science flights!!!!

## Slide 4: FORCAST Short Science I Image, December 2010
SS1
Orion Image

## Slide 5
FOR INTERNAL PROGRAM USE ONLY. DO NOT DISTRIBUTE.

## Slide 7: Recent and Upcoming Events
Ground turn loads test with aircraft at Dryden, March 14
Additional open Door Envelope Expansion flight; March 15
Re-install GREAT; March 18
Tech Brief for Short Science 2 flight series; March 24
RVSM certification; March 31
Observatory Characterization Flight with GREAT; March 31
Short Science #2 flights start; April 5
LN2 pre-cooling independent safety review; April 13
Remove GREAT; April 14
FORCAST testing with SS#2 MCCS build; mid April
PPBE Submission to SMD; May 5, 2011
Start of Basic Science #1 with FORCAST; early May
Second Generation Instrument AO released; early Summer
Occultation June 23 and June 27
Start of BS#2 with GREAT; early July
Germany Deployment; mid September
Possible Washington DC stop
HIPO/FLITCAM commissioning and telescope V&V Fall 2011
Segment III downtime start, mid November

## Slide 8: Segment 2 – With Occultation, 2 attempts
Avionics Upgrade
Cavity Insulation
Mirror Coating
MCCS Upgrade
 | Observing Flights
 | Instrumentation Commissioning
 | Platform Flights
 | Aircraft maintenance / Observatory upgrade
 | Fixed Dates
GREAT Line Ops 3/29/11
(Completed)
Short Science 2 Start 4/5/11
(Completed)
Basic Science Start 5/5/11
TA V&V A/C Performance Flights Start 8/24/11
Open Door Flight Test Complete 11/10/11
Occultation Decision Point
Remove HIPO/
Install GREAT
Occultation Opportunities
6/22/11 & 6/26/11(Sunday)
Germany Deployment
9/15/11
Remove GREAT
7/29/11
Maint. Req. 8/1/11
Maint. Req. 11/11/11
Install HIPO/FDC
H - Holiday
T – Flight day is highlighted
IMS Reference: SOFIA_IMS110404JP.mpp
Created April 4th, 2011
Media Day
6/8/11

## Slide 9: Segment 3
 | Observing Flights
 | Instrumentation Commissioning
 | Platform Flights
 | Aircraft maintenance / Observatory upgrade
FOC September 25, 2012
Heading Turner
TA Improvements?
OBDMA
Ground Cooling
SATCOM installation
TA Improvements?
TA Improvements?
TA Improvements?
TA Improvements?
TA Improvements?
WVM Upgrade
TA Improvements?
2 week southern hemisphere deployment
Research Hours
CY2012 – 245
CY2013 – 640
CY2014 – 836
SS3SO 7/13/12
RSSO 9/8/14
IMS Reference: SOFIA_IMS110404JP.mpp
Created April 4th, 2011

## Slide 10: Operational Phase
 | Observing Flights
 | Instrumentation Commissioning
 | Platform Flights
 | Aircraft maintenance / Observatory upgrade
TA Improvements?
TA Improvements?
TA Improvements?
TA Improvements?
TA Improvements?
TA Improvements?
TA Improvements?
TA Improvements?
Research Hours
CY2015 – 961
CY2016 – 961
CY2017 – 992
TA Improvements?
TA Improvements?
2 week southern hemisphere deployment
IMS Reference: SOFIA_IMS110404JP.mpp
Created April 4th, 2011

## Slide 11: SOFIA – Go For Early Science!